## BlankForm
FIELD REPORT |  | Report By:
Project: |  | Date:
SBC #: |  | Report No:
Time: | Weather: |  |  | Temp:
Work in Progress; Work Force; % Complete; Observations; Present at site
Action Items:
Page:
`

## Example
FIELD REPORT |  |  |  | Report By: | J. Smith, Architect
Project: | Campus Center |  |  | Date: | 05/15/2005
SBC #: | 166/ 000-05-05 |  |  | Report No: | A 15
Time: | 10:00 |  | Weather: | Clear and light wind |  | Temp: | 58 .
Work in Progress; Work Force; % Complete; Observations; Present at site
Bldg. A - | 6 masons placing brick @ north wall at administration area
4 masons placing CMU at interior walls
4 steel erectors placing roof joists
Brick work is about 50 % complete
CMU is 75 % complete
Roof steel is just starting, about 10 % complete
1. Brick ties are being placed per specs
2. Flashing at lintels per spec
3. Weeps are being placed above doors as required
4. CMU lintels extend to 8" bearing both sides of openings
Bldg. B | 4 laborers placing concrete @ footings at south wall
3 laborers placing concrete at slab-on-grade at front of building
2 representatives from the Testing Lab are present, sampling concrete
Footings are 95 % complete, with only the current pour remaining
Floor slab is 40% complete
1. Rebar at footings is elevated as required
2. Reinforcing mesh at slab is being raised as required. Observed placing
concrete at slab on grade at bldg.front. The mesh is being secured
during placing, preventing it from falling to the bottom of the pour
3. Observed concrete testing from trucks at specified intervals.
Observed three slump tests. All appeared to have appropriate slumps.
Action Items:
Contractor 1. Remove soil from streets around building
2. Minimize dust from piles being driven at Building C
3. Secure back of site where fence is down.
Campus 1. Block off parking spaces at site entry to ease large truck entry to site
2. Issue memo asking students not to jump fence to cut across work area.
[5 empty] | Page: | One of One