## BlankForm
| ACTION ITEM LOG Date: | O-Owner |  | TBR-OFD
| Project: | D-Designer
C-Contractor
SBC#:
|  | Action | Start | Due | Finish | Days
# | Action Item Description | By | Date | Date | Date | Out
Page of

## Example
| ACTION ITEM LOG Date: 05/15/05 | O-Owner |  | TBR-OFD
J.Jones, Con. Rep. 865-555-1212
| Project: Campus Center NWTU | D-Designer |  | TRN Design Group
| Nortonville, TN |  | S.Smith, Architect 423-555-7676
|  | C-Contractor |  | TN Constructors
| SBC#: 166/000-05-05b |  | G.Harms, Super. 865-555-8989
|  | Action | Start | Due | Finish | Days
# | Action Item Description | By | Date | Date | Date | Out
75 | Submit color samples for Terrazzo | C | 2005-04-15 | 2005-04-29 | 2005-04-30 | 15
76 | Construction Rep to review recommendation for CO # 3 | O | 2005-04-15 | 2005-04-20 | 2005-04-20 | 5
77 | Submit security system data | C | 2005-04-22 | 2005-05-06 |  | 23
78 | Submit recommendation letter for RFPs 25 & 26 | D | 2005-04-22 | 2005-04-29 | 2005-05-05 | 14
79 | Review pricing for RFP's 19 & 24 submitted by contractor | D | 2005-05-01 | 2005-05-08 |  | 14
80 | Pricing for RFP 27 to be resubmitted on SBC breakdown form | C | 2005-05-05 | 2005-05-04 |  | 10
81 | Review proposed Pay Application #4 when faxed by | D | 2005-05-05 | 2005-05-10 | 2005-05-15 | 10
contractor three days before next meeting
82 | Contractor is due only 5% on subs work; needs to revise | C | 2005-05-05 | 2005-05-10 |  | 10
pricing for RFP 30 and resubmit ASAP
83 | Contractor needs answers to RFI's 53 & 54 ASAP | D | 2005-05-05 | 2005-05-08 |  | 10
84 | Mark up as-built drawings showing changes per ASI #23 | C | 2005-05-15 | 2005-05-29
85 | Contractor ro develop a recovery schedule in Phase 1. | C | 2005-05-15 | 2005-05-20
86 | Campus to coordinate w/ users for shut down of power | O | 1999-05-15 | 1999-05-22
87 | Recovery schedule meeting to be: Monday at 1:00pm | C | 2005-05-15 | 2005-05-20
88 | TBR to discuss w/ Fire Marshal issues noted on his | O | 2005-05-15 | 2005-05-15
field report dated 5/07/05
89 | Review contractor RFP request for work related to ASI #45 | D | 2005-05-15 | 2005-05-18
90 | Revise Meeting Minutes #8 per progress meeting | D | 2005-05-15 | 2005-05-29
91 | Field Report to be issued for todays walk-thru | D | 2005-05-15 | 2005-05-29
Page 1 of 1