## HPBr Checklist
High Performance Building Requirements v1.01 | [19 empty] | Project Team Representatives | Initials
CHECKLIST / TRACKING FORM | [17 empty] | O | - | Owner
Phase | Targeted Points | SBC Number: | [15 empty] | C | - | Contractor |  |  |  |  | Yes
|  | Project Name: | [15 empty] | ME | - | Mechanical Engineer |  |  | Category A |  | No
Applicable | 0 | Date: | [15 empty] | EE | - | Electrical Engineer |  |  | Category B | Programming
Minimum | 0 | Project Type: | [15 empty] | CE | - | Civil Engineer |  |  | Category C | Schematic Design
Not Applicable | 0 | Project Phase: | [15 empty] | A | - | Architect |  |  | Required | Detailed Design
Programming | 0 | Category from Applicability Tree: | Category C | [14 empty] | Other | - | Other |  |  | Priority 1 | Construction Documentation
SD | 0 | [21 empty] | Priority 2 | Closeout
DD | 0 | [21 empty] | N/A
CD | 0
Closeout | 0
[5 empty] | Programming |  |  | SD |  |  | DD |  |  | CD |  |  | Closeout
|  |  |  | Checklist Total | 0 | 0 | 104 | 0 | 0 | 104 | 0 | 0 | 104 | 0 | 0 | 104 | 0 | 0 | 104
22 Points |  |  | Land Management | LM Total: | 0 | 0 | 22 | 0 | 0 | 22 | 0 | 0 | 22 | 0 | 0 | 22 | 0 | 0 | 22 |  | Primary Credit Responsibility
Possible Points | Credit ID | Applicable to Building/Site Scope? | Description | Level: | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Comment: Describe implementation approach for each pursued credit. If credits are not pursued, provide justification. | Role | Initials
1 | LM1.1 |  | Site Selection - Reuse Existing Buildings | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
1 | LM1.2 |  | Site Selection - Show preference for building on developed sites: Preserve farmland/habitat, wetlands, floodplains, public parkland | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
1 | LM1.3 |  | Site Selection - Brownfield Redevelopment - Remediate and Restore contaminated sites when possible | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
1 | LM1.4 |  | Site Selection - Urban Development - Locate building within existing infrastructure | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
1 | LM2.1 |  | Site Disturbance - Sediment and Erosion control during construction | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | C | 0
1 | LM2.2 |  | Site Disturbance - Limit site disturbance during construction to minimum development footprint | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | CE | 0
1 | LM3.1 |  | Transportation - Plan for access to public transportation | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
1 | LM3.2 |  | Transportation - Provide bicycle storage for 5% of building occupants and shower/changing facilities for 0.5% of FTE occupants | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | CE | 0
1 | LM3.3 |  | Transportation - Plan site to include preferred parking for carpooling for 5% of all spaces provided | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | CE | 0
1 | LM3.4 |  | Transportation - Plan site to include preferred parking for low-emitting/fuel efficient vehicles for 5% of all spaces provided | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | CE | 0
1 | LM4.1 |  | Landscape Design - Maximize vegetated open space | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
1 | LM4.2 |  | Landscape Design - Native and drought tolerant planting | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
1 | LM5.1 |  | Heat Island Reduction - Non roof surface reflectivity and shading | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | CE | 0
1 | LM5.2 |  | Heat Island Reduction - Reflective roof materials | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | LM6.1 |  | Stormwater Design - Post development discharge rate and volume not to exceed Pre-development rate | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | CE | 0
2 | LM6.2 |  | Stormwater Design - Reduce discharge rate and volume 25% on previously developed sites. | Priority 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | CE | 0
1 | LM6.3 |  | Stormwater Design - Design to remove 80% Total Suspended solids from the average annual rainfall event. Verify local requirements. | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | CE | 0
1 | LM6.4 |  | Stormwater Design - Design per TDEC BMP References | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | CE | 0
1 | LM7.1 |  | Exterior Site Lighting - Design exterior lighting power to be 10% less than is allowed by ASHRAE 90.1-2010, Section 9.4.3 | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | EE | 0
1 | LM7.2 |  | Exterior Site Lighting - Locate fixtures to minimize illuminance above the horizontal plane | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | EE | 0
1 | LM7.3 |  | Exterior Site Lighting - Locate exterior fixtures to minimize light trespass at property lines. Document foot-candle levels at site boundary | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | EE | 0
6 Points |  |  | Water Effciency | WE Total: | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 |  | Primary Credit Responsibility
Possible Points | Credit ID | Applicable to Building/Site Scope? | Description | Level: | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Comment: Describe implementation approach for each pursued credit. If credits are not pursued, provide justification. | Role | Initials
1 | WE1.1 |  | Water Efficient Landscaping, Utilize efficient irrigation technologies and planting measures | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | WE.1.2 |  | Water Efficient Landscaping, Non potable sources or no irrigation | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | WE2.1 |  | Wastewater Treatment & Conveyance: On site treatment | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | WE2.2 |  | Wastewater Treatment & Conveyance: Utilize non potable water | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | WE3.1 |  | Water Use Reduction - Fixture flow and flush rates | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | WE3.2 |  | Water Use Reduction - Utilize auto-flow / auto-flush valves | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
37 Points |  |  | Energy Efficiency | EE Total: | 0 | 0 | 37 | 0 | 0 | 37 | 0 | 0 | 37 | 0 | 0 | 37 | 0 | 0 | 37 |  | Primary Credit Responsibility
Possible Points | Credit ID | Applicable to Building/Site Scope? | Description | Level: | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Comment: Describe implementation approach for each pursued credit. If credits are not pursued, provide justification. | Role | Initials
1 | EE1.1 |  | Commissioning - Basic commissioning process | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
3 | EE1.2 |  | Commissioning - Advanced commissioning process | Priority 1 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3
1 | EE2.1 |  | Energy Efficient Purchasing Policy - Energy Star qualified appliances & equipment | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
1 | EE3.1 |  | Energy Efficiency - Schematic Design energy modeling | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
1 | EE3.2 |  | Energy Efficiency - Life Cycle Cost Analysis | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
1 | EE3.3 |  | Minimum Energy Performance - all projects to demonstrate compliance with ASHRAE 90.1-2010, according to project scope | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
8 | EE3.4 |  | Improved Energy Performance - energy model is used during design, and final design demonstrates energy cost savings that exceed those required by the Minimum Energy Performance credit (EE3.3) | Priority 1 |  |  | 8 |  |  | 8 |  |  | 8 |  |  | 8 |  |  | 8 |  | Other | 0
5 | EE4.1 |  | Energy Efficiency in Existing Buildings - Lighting Power Reduction | Priority 1 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  | EE | 0
2 | EE4.2 |  | Energy Efficiency in Existing Buildings - Daylight Harvesting Controls | Priority 1 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | EE | 0
2 | EE4.3 |  | Energy Efficiency in Existing Buildings - Vacancy sensor-controlled lighting | Priority 1 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | EE | 0
2 | EE4.4 |  | Energy Efficiency in Existing Buildings - High efficiency HVAC Equipment | Priority 1 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | ME | 0
1 | EE5.1 |  | Energy Metering, Monitoring and Reporting: Building-Level Metering | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
3 | EE5.2 |  | Energy Metering, Monitoring and Reporting: System level energy metering with measurement and verification - New Construction | Priority 1 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  | Other | 0
3 | EE5.3 |  | Energy Metering, Monitoring and Reporting: System level energy metering with measurement and verification - Existing Buildings | Priority 1 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  | Other | 0
1 | EE6.1 |  | Long-Term Energy Reporting - Maintain energy and water consumption data in Energy Star Portfolio Manager | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
1 | EE7.1 |  | Renewable Energy - Investigate life-cycle cost effectiveness of on-site renewable energy | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
1 | EE7.2 |  | Renewable Energy - Provide Renewable Energy Credits (RECs) equal to 10% of annual site electricity through TVA or RECs equal to 35% from another source | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
15 Points |  |  | Materials and Resources | MR Total: | 0 | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 15 |  | Primary Credit Responsibility
Possible Points | Credit ID | Applicable to Building/Site Scope? | Description | Level: | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Comment: Describe implementation approach for each pursued credit. If credits are not pursued, provide justification. | Role | Initials
1 | MR1.1 |  | Recycling Collection and Storage | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
3 | MR2.1 |  | Construction Waste Management (50%, 75%, 95%) | Priority 1 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  | C | 0
1 | MR3.1 |  | Sustainable Materials: Recycled content 10% | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | MR3.2 |  | Sustainable Materials: Recycled content 20% | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
3 | MR3.3 |  | Sustainable Materials: Tennessee Produced Materials (non-wood) - Harvested AND manufactured in state - 10% of total cost. Harvested OR manufactured in TN, 50% of product cost contributes to credit. | Priority 2 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  | A | 0
3 | MR3.4 |  | Sustainable Materials: Tennessee Produced Wood Products -Wood materials harvested AND manufactured in state - 50% of wood products. When harvested OR manufactured in state, 50% of material cost contributes to credit. | Priority 2 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  | A | 0
1 | MR3.5 |  | Sustainable Materials: Regional materials - 20% | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | MR3.6 |  | Sustainable Materials: Material reuse | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | MR3.7 |  | Sustainable Materials: Rapidly renewables | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
19 Points |  |  | Indoor Environmental Quality | EQ Total: | 0 | 0 | 19 | 0 | 0 | 19 | 0 | 0 | 19 | 0 | 0 | 19 | 0 | 0 | 19 |  | Primary Credit Responsibility
Possible Points | Credit ID | Applicable to Building/Site Scope? | Description | Level: | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Comment: Describe implementation approach for each pursued credit. If credits are not pursued, provide justification. | Role | Initials
1 | EQ1.1 |  | Tobacco Smoke Control | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | O | 0
1 | EQ2.1 |  | Minimum Ventilation: Design to meet ASHRAE 62.1-2007 or 2012 IMC | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | EQ3.1 |  | Outdoor Air Delivery Monitoring: Provide a direct outdoor airflow measurement device | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | EQ4.1 |  | CO2 Monitoring: Provide CO2 monitors in all high occupancy areas | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | EQ5.1 |  | Air Quality Management: During construction | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | C | 0
1 | EQ5.2 |  | Air Quality Management: Before occupancy | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | C | 0
1 | EQ6.1 |  | Material VOC Limits: Adhesives and sealants | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | EQ6.2 |  | Material VOC Limits: Paints | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | EQ6.3 |  | Material VOC Limits: Coatings and anti-corrosive paints | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | EQ6.4 |  | Material VOC Limits: Flooring systems | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | EQ6.5 |  | Material VOC Limits: Composite wood and agrifiber | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | EQ7.1 |  | Pollutant Control: Entryway systems | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | EQ7.2 |  | Pollutant Control: Hazardous material storage | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | EQ7.3 |  | Pollutant Control: Filtration media | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | EQ8.1 |  | Thermal Comfort: Design to meet ASHRAE Standard 55-2004 | Required |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | EQ9.1 |  | Individual Occupant System Controls: Lighting controls | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | EE | 0
1 | EQ9.2 |  | Individual Occupant System Controls: Thermal comfort | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | ME | 0
1 | EQ10.1 |  | Daylight to Occupied spaces | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
1 | EQ11.1 |  | Views from Occupied spaces | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | A | 0
5 Points |  |  | Innovation in Design and Construction | ID Total: | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 5 |  | Primary Credit Responsibility
Possible Points | Credit ID | Applicable to Building/Site Scope? | Description | Level: | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Yes | Maybe | No | Comment: Describe implementation approach for each pursued credit. If credits are not pursued, provide justification. | Role | Initials
1 | ID1.1 |  | Innovation in Design: Provide Specific Title | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
1 | ID1.2 |  | Innovation in Design: Provide Specific Title | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
1 | ID1.3 |  | Innovation in Design: Provide Specific Title | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
1 | ID1.4 |  | Innovation in Design: Provide Specific Title | Priority 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
1 | ID2.1 |  | Environmentally Accredited Design Team | Priority 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | Other | 0
|  |  |  | Checklist Total: | 0 | 0 | 104 | 0 | 0 | 104 | 0 | 0 | 104 | 0 | 0 | 104 | 0 | 0 | 104
Note on V2: Enter the initials of the project team individuals who will be primarily responsible for signing off on credit compliance.
Note on B3: During each project phase, review the Yes, Maybe, and No credits and fill in a target point total to design towards.
Note on F11: A point allocation error will appear if more than the maximum points for a credit are claimed
Note on C16: The Owner will select Yes/No depending on whether the credit is applicable to the project scope. Where "No" is selected, the row's text will turn gray.

## Credit Lookup (hidden)
Credit ID | Description | CreditID_Description
LM1.1 | Site Selection - Reuse Existing Buildings | LM1.1 Site Selection - Reuse Existing Buildings
LM1.2 | Site Selection - Show preference for building on developed sites: Preserve farmland/habitat, wetlands, floodplains, public parkland | LM1.2 Site Selection - Show preference for building on developed sites: Preserve farmland/habitat, wetlands, floodplains, public parkland
LM1.3 | Site Selection - Brownfield Redevelopment - Remediate and Restore contaminated sites when possible | LM1.3 Site Selection - Brownfield Redevelopment - Remediate and Restore contaminated sites when possible
LM1.4 | Site Selection - Urban Development - Locate building within existing infrastructure | LM1.4 Site Selection - Urban Development - Locate building within existing infrastructure
LM2.1 | Site Disturbance - Sediment and Erosion control during construction | LM2.1 Site Disturbance - Sediment and Erosion control during construction
LM2.2 | Site Disturbance - Limit site disturbance during construction to minimum development footprint | LM2.2 Site Disturbance - Limit site disturbance during construction to minimum development footprint
LM3.1 | Transportation - Plan for access to public transportation | LM3.1 Transportation - Plan for access to public transportation
LM3.2 | Transportation - Provide bicycle storage for 5% of building occupants and shower/changing facilities for 0.5% of FTE occupants | LM3.2 Transportation - Provide bicycle storage for 5% of building occupants and shower/changing facilities for 0.5% of FTE occupants
LM3.3 | Transportation - Plan site to include preferred parking for carpooling for 5% of all spaces provided | LM3.3 Transportation - Plan site to include preferred parking for carpooling for 5% of all spaces provided
LM3.4 | Transportation - Plan site to include preferred parking for low-emitting/fuel efficient vehicles for 5% of all spaces provided | LM3.4 Transportation - Plan site to include preferred parking for low-emitting/fuel efficient vehicles for 5% of all spaces provided
LM4.1 | Landscape Design - Maximize vegetated open space | LM4.1 Landscape Design - Maximize vegetated open space
LM4.2 | Landscape Design - Native and drought tolerant planting | LM4.2 Landscape Design - Native and drought tolerant planting
LM5.1 | Heat Island Reduction - Non roof surface reflectivity and shading | LM5.1 Heat Island Reduction - Non roof surface reflectivity and shading
LM5.2 | Heat Island Reduction - Reflective roof materials | LM5.2 Heat Island Reduction - Reflective roof materials
LM6.1 | Stormwater Design - Post development discharge rate and volume not to exceed Pre-development rate | LM6.1 Stormwater Design - Post development discharge rate and volume not to exceed Pre-development rate
LM6.2 | Stormwater Design - Reduce discharge rate and volume 25% on previously developed sites. | LM6.2 Stormwater Design - Reduce discharge rate and volume 25% on previously developed sites.
LM6.3 | Stormwater Design - Design to remove 80% Total Suspended solids from the average annual rainfall event. Verify local requirements. | LM6.3 Stormwater Design - Design to remove 80% Total Suspended solids from the average annual rainfall event. Verify local requirements.
LM6.4 | Stormwater Design - Design per TDEC BMP References | LM6.4 Stormwater Design - Design per TDEC BMP References
LM7.1 | Exterior Site Lighting - Design exterior lighting power to be 20% less than is allowed by ASHRAE 90.1-2007 | LM7.1 Exterior Site Lighting - Design exterior lighting power to be 20% less than is allowed by ASHRAE 90.1-2007
LM7.2 | Exterior Site Lighting - Locate fixtures to minimize illuminance above the horizontal plane | LM7.2 Exterior Site Lighting - Locate fixtures to minimize illuminance above the horizontal plane
LM7.3 | Exterior Site Lighting - Locate exterior fixtures to minimize light trespass at property lines. Document foot-candle levels at site boundary | LM7.3 Exterior Site Lighting - Locate exterior fixtures to minimize light trespass at property lines. Document foot-candle levels at site boundary
WE1.1 | Water Efficient Landscaping, Utilize efficient irrigation technologies and planting measures | WE1.1 Water Efficient Landscaping, Utilize efficient irrigation technologies and planting measures
WE.1.2 | Water Efficient Landscaping, Non potable sources or no irrigation | WE.1.2 Water Efficient Landscaping, Non potable sources or no irrigation
WE2.1 | Wastewater Treatment & Conveyance: On site treatment | WE2.1 Wastewater Treatment & Conveyance: On site treatment
WE2.2 | Wastewater Treatment & Conveyance: Utilize non potable water | WE2.2 Wastewater Treatment & Conveyance: Utilize non potable water
WE3.1 | Water Use Reduction - Fixture flow and flush rates | WE3.1 Water Use Reduction - Fixture flow and flush rates
WE3.2 | Water Use Reduction - Utilize auto-flow / auto-flush valves | WE3.2 Water Use Reduction - Utilize auto-flow / auto-flush valves
EE1.1 | Commissioning - Basic commissioning process | EE1.1 Commissioning - Basic commissioning process
EE1.2 | Commissioning - Advanced commissioning process | EE1.2 Commissioning - Advanced commissioning process
EE2.1 | Energy Efficient Purchasing Policy - Energy Star qualified appliances & equipment | EE2.1 Energy Efficient Purchasing Policy - Energy Star qualified appliances & equipment
EE3.1 | Energy Efficiency - in New Construction and Renovation Projects; Schematic Design energy modeling | EE3.1 Energy Efficiency - in New Construction and Renovation Projects; Schematic Design energy modeling
EE3.2 | Energy Efficiency - Life Cycle Cost Analysis | EE3.2 Energy Efficiency - Life Cycle Cost Analysis
EE3.3 | Minimum Energy Performance - all projects to demonstrate compliance with ASHRAE 90.1-2010, according to project scope | EE3.3 Minimum Energy Performance - all projects to demonstrate compliance with ASHRAE 90.1-2010, according to project scope
EE3.4 | Improved Energy Performance - in New Construction & Renovation Projects points are available if the energy model is used during design and final design demonstrates energy cost savings that exceed those required by the Minimum Energy Performance credit (EE3.3) | EE3.4 Improved Energy Performance - in New Construction & Renovation Projects points are available if the energy model is used during design and final design demonstrates energy cost savings that exceed those required by the Minimum Energy Performance credit (EE3.3)
EE4.1 | Energy Efficiency in Existing Buildings - Lighting Power Reduction | EE4.1 Energy Efficiency in Existing Buildings - Lighting Power Reduction
EE4.2 | Energy Efficiency in Existing Buildings - Daylight Harvesting Controls | EE4.2 Energy Efficiency in Existing Buildings - Daylight Harvesting Controls
EE4.3 | Energy Efficiency in Existing Buildings - Occupancy sensor-controlled lighting | EE4.3 Energy Efficiency in Existing Buildings - Occupancy sensor-controlled lighting
EE4.4 | Energy Efficiency in Existing Buildings - High efficiency HVAC Equipment | EE4.4 Energy Efficiency in Existing Buildings - High efficiency HVAC Equipment
EE5.1 | Energy Metering, Monitoring and Reporting: Building-Level Metering | EE5.1 Energy Metering, Monitoring and Reporting: Building-Level Metering
EE5.2 | Energy Metering, Monitoring and Reporting: System level energy metering with measurement and verification - New Construction | EE5.2 Energy Metering, Monitoring and Reporting: System level energy metering with measurement and verification - New Construction
EE5.3 | Energy Metering, Monitoring and Reporting: System level energy metering with measurement and verification - Existing Buildings | EE5.3 Energy Metering, Monitoring and Reporting: System level energy metering with measurement and verification - Existing Buildings
EE6.1 | Long-Term Energy Reporting - Maintain energy and water consumption data in Energy Star Portfolio Manager | EE6.1 Long-Term Energy Reporting - Maintain energy and water consumption data in Energy Star Portfolio Manager
EE7.1 | Renewable Energy - Investigate life-cycle cost effectiveness of on-site renewable energy | EE7.1 Renewable Energy - Investigate life-cycle cost effectiveness of on-site renewable energy
EE7.2 | Renewable Energy - Provide Renewable Energy Credits (RECs) equal to 10% of annual site electricity through TVA or RECs equal to 35% from another source | EE7.2 Renewable Energy - Provide Renewable Energy Credits (RECs) equal to 10% of annual site electricity through TVA or RECs equal to 35% from another source
MR1.1 | Recycling Storage and Collection | MR1.1 Recycling Storage and Collection
MR2.1 | Construction Waste Management (50%, 75%, 95%) | MR2.1 Construction Waste Management (50%, 75%, 95%)
MR3.1 | Sustainable Materials: Recycled content 10% | MR3.1 Sustainable Materials: Recycled content 10%
MR3.2 | Sustainable Materials: Recycled content 20% | MR3.2 Sustainable Materials: Recycled content 20%
MR3.3 | Sustainable Materials: Tennessee Produced Materials (non-wood) - Harvested AND manufactured in state - 10% of total cost. Harvested OR manufactured in TN, 50% of product cost contributes to credit. | MR3.3 Sustainable Materials: Tennessee Produced Materials (non-wood) - Harvested AND manufactured in state - 10% of total cost. Harvested OR manufactured in TN, 50% of product cost contributes to credit.
MR3.4 | Sustainable Materials: Tennessee Produced Wood Products -Wood materials harvested AND manufactured in state - 50% of wood products. When harvested OR manufactured in state, 50% of material cost contributes to credit. | MR3.4 Sustainable Materials: Tennessee Produced Wood Products -Wood materials harvested AND manufactured in state - 50% of wood products. When harvested OR manufactured in state, 50% of material cost contributes to credit.
MR3.5 | Sustainable Materials: Regional materials - 20% | MR3.5 Sustainable Materials: Regional materials - 20%
MR3.6 | Sustainable Materials: Material reuse | MR3.6 Sustainable Materials: Material reuse
MR3.7 | Sustainable Materials: Rapidly renewables | MR3.7 Sustainable Materials: Rapidly renewables
EQ1.1 | Tobacco Smoke Control | EQ1.1 Tobacco Smoke Control
EQ2.1 | Minimum Ventilation: Design to meet ASHRAE 62.1-2007 or 2012 IMC | EQ2.1 Minimum Ventilation: Design to meet ASHRAE 62.1-2007 or 2012 IMC
EQ3.1 | Outdoor Air Delivery Monitoring: Provide a direct outdoor airflow measurement device | EQ3.1 Outdoor Air Delivery Monitoring: Provide a direct outdoor airflow measurement device
EQ4.1 | CO2 Monitoring: Provide CO2 monitors in all high occupancy areas | EQ4.1 CO2 Monitoring: Provide CO2 monitors in all high occupancy areas
EQ5.1 | Air Quality Management: During construction | EQ5.1 Air Quality Management: During construction
EQ5.2 | Air Quality Management: Before occupancy | EQ5.2 Air Quality Management: Before occupancy
EQ6.1 | Material VOC Limits: Adhesives and sealants | EQ6.1 Material VOC Limits: Adhesives and sealants
EQ6.2 | Material VOC Limits: Paints | EQ6.2 Material VOC Limits: Paints
EQ6.3 | Material VOC Limits: Coatings and anti-corrosive paints | EQ6.3 Material VOC Limits: Coatings and anti-corrosive paints
EQ6.4 | Material VOC Limits: Flooring systems | EQ6.4 Material VOC Limits: Flooring systems
EQ6.5 | Material VOC Limits: Composite wood and agrifiber | EQ6.5 Material VOC Limits: Composite wood and agrifiber
EQ7.1 | Pollutant Control: Entryway systems | EQ7.1 Pollutant Control: Entryway systems
EQ7.2 | Pollutant Control: Hazardous material storage | EQ7.2 Pollutant Control: Hazardous material storage
EQ7.3 | Pollutant Control: Filtration media | EQ7.3 Pollutant Control: Filtration media
EQ8.1 | Thermal Comfort: Design to meet ASHRAE Standard 55-2004 | EQ8.1 Thermal Comfort: Design to meet ASHRAE Standard 55-2004
EQ9.1 | Individual Occupant System Controls: Lighting | EQ9.1 Individual Occupant System Controls: Lighting
EQ9.2 | Individual Occupant System Controls: Thermal comfort | EQ9.2 Individual Occupant System Controls: Thermal comfort
EQ10.1 | Daylight to Occupied spaces | EQ10.1 Daylight to Occupied spaces
EQ11.1 | Views from Occupied spaces | EQ11.1 Views from Occupied spaces
ID1.1 | Innovation in Design: Provide Specific Title | ID1.1 Innovation in Design: Provide Specific Title
ID1.2 | Innovation in Design: Provide Specific Title | ID1.2 Innovation in Design: Provide Specific Title
ID1.3 | Innovation in Design: Provide Specific Title | ID1.3 Innovation in Design: Provide Specific Title
ID1.4 | Innovation in Design: Provide Specific Title | ID1.4 Innovation in Design: Provide Specific Title
ID2.1 | Environmentally Accredited Design Team | ID2.1 Environmentally Accredited Design Team

## Credit Verification
|  | Credit Verification Form | Phase:
HPBr Points Required |  | TN High Performance Building Requirements |  | HPBr Points Achieved
0 |  | In accordance with the State Architect's office, a copy of this form must be submitted at the end of each project phase and accompany required Project Closeout documents. Acceptance by the State Project Manager is required upon review of completed Credit Verification Form. |  | 0
Designated Project Team Member | Initials | Team Member Name |  | Date
Owner: | 0 | [sign/type team member name as verification that initialed credits are COMPLETE]
Contractor: | 0 | [sign/type team member name as verification that initialed credits are COMPLETE]
Mech. Eng.: | 0 | [sign/type team member name as verification that initialed credits are COMPLETE]
Elec. Eng.: | 0 | [sign/type team member name as verification that initialed credits are COMPLETE]
Civil Eng.: | 0 | [sign/type team member name as verification that initialed credits are COMPLETE]
Architect: | 0 | [sign/type team member name as verification that initialed credits are COMPLETE]
Other: | 0 | [sign/type team member name as verification that initialed credits are COMPLETE]
0 |  | Land Management
# Points | Credit ID | Description | Credit Level: | Sign-Off (linked from HPBr Checklist)
0 | LM1.1 | Site Selection - Reuse Existing Buildings | Priority 2 | N/A
0 | LM1.2 | Site Selection - Show preference for building on developed sites: Preserve farmland/habitat, wetlands, floodplains, public parkland | Priority 1 | N/A
0 | LM1.3 | Site Selection - Brownfield Redevelopment - Remediate and Restore contaminated sites when possible | Priority 2 | N/A
0 | LM1.4 | Site Selection - Urban Development - Locate building within existing infrastructure | Priority 1 | N/A
0 | LM2.1 | Site Disturbance - Sediment and Erosion control during construction | Required | N/A
0 | LM2.2 | Site Disturbance - Limit site disturbance during construction to minimum development footprint | Priority 1 | N/A
0 | LM3.1 | Transportation - Plan for access to public transportation | Priority 2 | N/A
0 | LM3.2 | Transportation - Provide bicycle storage for 5% of building occupants and shower/changing facilities for 0.5% of FTE occupants | Priority 2 | N/A
0 | LM3.3 | Transportation - Plan site to include preferred parking for carpooling for 5% of all spaces provided | Priority 2 | N/A
0 | LM3.4 | Transportation - Plan site to include preferred parking for low-emitting/fuel efficient vehicles for 5% of all spaces provided | Priority 2 | N/A
0 | LM4.1 | Landscape Design - Maximize vegetated open space | Priority 2 | N/A
0 | LM4.2 | Landscape Design - Native and drought tolerant planting | Required | N/A
0 | LM5.1 | Heat Island Reduction - Non roof surface reflectivity and shading | Priority 1 | N/A
0 | LM5.2 | Heat Island Reduction - Reflective roof materials | Priority 2 | N/A
0 | LM6.1 | Stormwater Design - Post development discharge rate and volume not to exceed Pre-development rate | Priority 1 | N/A
0 | LM6.2 | Stormwater Design - Reduce discharge rate and volume 25% on previously developed sites. | Priority 2 | N/A
0 | LM6.3 | Stormwater Design - Design to remove 80% Total Suspended solids from the average annual rainfall event. Verify local requirements. | Priority 1 | N/A
0 | LM6.4 | Stormwater Design - Design per TDEC BMP References | Required | N/A
0 | LM7.1 | Exterior Site Lighting - Design exterior lighting power to be 10% less than is allowed by ASHRAE 90.1-2010, Section 9.4.3 | Priority 2 | N/A
0 | LM7.2 | Exterior Site Lighting - Locate fixtures to minimize illuminance above the horizontal plane | Priority 1 | N/A
0 | LM7.3 | Exterior Site Lighting - Locate exterior fixtures to minimize light trespass at property lines. Document foot-candle levels at site boundary | Priority 1 | N/A
0 |  | Water Efficiency
# Points | Credit ID | Description | Credit Level | Sign-Off (from HPBr Checklist)
0 | WE1.1 | Water Efficient Landscaping, Utilize efficient irrigation technologies and planting measures | Required | N/A
0 | WE.1.2 | Water Efficient Landscaping, Non potable sources or no irrigation | Priority 1 | N/A
0 | WE2.1 | Wastewater Treatment & Conveyance: On site treatment | Priority 2 | N/A
0 | WE2.2 | Wastewater Treatment & Conveyance: Utilize non potable water | Priority 2 | N/A
0 | WE3.1 | Water Use Reduction - Fixture flow and flush rates | Required | N/A
0 | WE3.2 | Water Use Reduction - Utilize auto-flow / auto-flush valves | Priority 2 | N/A
0 |  | Energy Efficiency
# Points | Credit ID | Description | Credit Level | Sign-Off (from HPBr Checklist)
0 | EE1.1 | Commissioning - Basic commissioning process | Required | N/A
0 | EE1.2 | Commissioning - Advanced commissioning process | Priority 1 | N/A
0 | EE2.1 | Energy Efficient Purchasing Policy - Energy Star qualified appliances & equipment | Required | N/A
0 | EE3.1 | Energy Efficiency - Schematic Design energy modeling | Required | N/A
0 | EE3.2 | Energy Efficiency - Life Cycle Cost Analysis | Priority 1 | N/A
0 | EE3.3 | Minimum Energy Performance - all projects to demonstrate compliance with ASHRAE 90.1-2010, according to project scope | Required | N/A
0 | EE3.4 | Improved Energy Performance - energy model is used during design, and final design demonstrates energy cost savings that exceed those required by the Minimum Energy Performance credit (EE3.3) | Priority 1 | N/A
0 | EE4.1 | Energy Efficiency in Existing Buildings - Lighting Power Reduction | Priority 1 | N/A
0 | EE4.2 | Energy Efficiency in Existing Buildings - Daylight Harvesting Controls | Priority 1 | N/A
0 | EE4.3 | Energy Efficiency in Existing Buildings - Vacancy sensor-controlled lighting | Priority 1 | N/A
0 | EE4.4 | Energy Efficiency in Existing Buildings - High efficiency HVAC Equipment | Priority 1 | N/A
0 | EE5.1 | Energy Metering, Monitoring and Reporting: Building-Level Metering | Priority 1 | N/A
0 | EE5.2 | Energy Metering, Monitoring and Reporting: System level energy metering with measurement and verification - New Construction | Priority 1 | N/A
0 | EE5.3 | Energy Metering, Monitoring and Reporting: System level energy metering with measurement and verification - Existing Buildings | Priority 1 | N/A
0 | EE6.1 | Long-Term Energy Reporting - Maintain energy and water consumption data in Energy Star Portfolio Manager | Priority 1 | N/A
0 | EE7.1 | Renewable Energy - Investigate life-cycle cost effectiveness of on-site renewable energy | Priority 1 | N/A
0 | EE7.2 | Renewable Energy - Provide Renewable Energy Credits (RECs) equal to 10% of annual site electricity through TVA or RECs equal to 35% from another source | Priority 2 | N/A
0 |  | Materials and Resources
# Points | Credit ID | Description | Credit Level | Sign-Off (from HPBr Checklist)
0 | MR1.1 | Recycling Collection and Storage | Required | N/A
0 | MR2.1 | Construction Waste Management (50%, 75%, 95%) | Priority 1 | N/A
0 | MR3.1 | Sustainable Materials: Recycled content 10% | Required | N/A
0 | MR3.2 | Sustainable Materials: Recycled content 20% | Priority 2 | N/A
0 | MR3.3 | Sustainable Materials: Tennessee Produced Materials (non-wood) - Harvested AND manufactured in state - 10% of total cost. Harvested OR manufactured in TN, 50% of product cost contributes to credit. | Priority 2 | N/A
0 | MR3.4 | Sustainable Materials: Tennessee Produced Wood Products -Wood materiasl harvested AND manufactured in state - 50% of wood products. When harvested OR manufactred in state, 50% of material cost contributes to credit. | Priority 2 | N/A
0 | MR3.5 | Sustainable Materials: Regional materials - 20% | Priority 2 | N/A
0 | MR3.6 | Sustainable Materials: Material reuse | Priority 2 | N/A
0 | MR3.7 | Sustainable Materials: Rapidly renewables | Priority 2 | N/A
0 |  | Indoor Environmental Quality
# Points | Credit ID | Description | Credit Level | Sign-Off (from HPBr Checklist)
0 | EQ1.1 | Tobacco Smoke Control | Required | N/A
0 | EQ2.1 | Minimum Ventilation: Design to meet ASHRAE 62.1-2007 or 2012 IMC | Required | N/A
0 | EQ3.1 | Outdoor Air Delivery Monitoring: Provide a direct outdoor airflow measurement device | Priority 2 | N/A
0 | EQ4.1 | CO2 Monitoring: Provide CO2 monitors in all high occupancy areas | Priority 2 | N/A
0 | EQ5.1 | Air Quality Management: During construction | Priority 1 | N/A
0 | EQ5.2 | Air Quality Management: Before occupancy | Priority 2 | N/A
0 | EQ6.1 | Material VOC Limits: Adhesives and sealants | Required | N/A
0 | EQ6.2 | Material VOC Limits: Paints | Required | N/A
0 | EQ6.3 | Material VOC Limits: Coatings and anti-corrosive paints | Required | N/A
0 | EQ6.4 | Material VOC Limits: Flooring systems | Required | N/A
0 | EQ6.5 | Material VOC Limits: Composite wood and agrifiber | Required | N/A
0 | EQ7.1 | Pollutant Control: Entryway systems | Priority 1 | N/A
0 | EQ7.2 | Pollutant Control: Hazardous material storage | Required | N/A
0 | EQ7.3 | Pollutant Control: Filtration media | Priority 1 | N/A
0 | EQ8.1 | Thermal Comfort: Design to meet ASHRAE Standard 55-2004 | Required | N/A
0 | EQ9.1 | Individual Occupant System Controls: Lighting controls | Priority 1 | N/A
0 | EQ9.2 | Individual Occupant System Controls: Thermal comfort | Priority 2 | N/A
0 | EQ10.1 | Daylight to Occupied spaces | Priority 1 | N/A
0 | EQ11.1 | Views from Occupied spaces | Priority 1 | N/A
0 |  | Innovation in Design and Construction
# Points | Credit ID | Description | Credit Level | Sign-Off (from HPBr Checklist)
0 | ID1.1 | Innovation in Design: Provide Specific Title | Priority 1 | N/A
0 | ID1.2 | Innovation in Design: Provide Specific Title | Priority 2 | N/A
0 | ID1.3 | Innovation in Design: Provide Specific Title | Priority 2 | N/A
0 | ID1.4 | Innovation in Design: Provide Specific Title | Priority 2 | N/A
0 | ID2.1 | Environmentally Accredited Design Team | Priority 1 | N/A
0 | Total HPBr Points Achieved by Project
Note on E18: Project Team Member initials will populate from the HPBr Checklist tab

## One-Time Completion Form
One-Time Completion Form
TN High Performance Building Requirements
**If a project has 5 (five) or fewer credits applicable to the project scope, this form may be used, signed, and filed (for future audit) by the Owner at the end of the Programming Phase. No further Credit Verification forms will need to be submitted.
Owner's Organization:
Owner Name:
Date:
SBC Number:
Project Name:
Project Scope/Description:
Number of Applicable Credits: (If there are no applicable credits, use Statement B)
Statement A: |  | After a complete and thorough review of the Tennessee High Performance Building Requirements Manual and Checklist, and in accordance with the Tennessee Code Annotated (TCA), the Owner has determined that there are between 5 (five) and 1 (one) Credits applicable to the scope of the examined project. The Project Team hereby commits to incorporating these selected Credits throughout the design and construction process and delivering a final product that is in full compliance with their requirements.
Credit Reference Number and Name
List Applicable Credits: | 1
2
3
4
5
Statement B: |  | After a complete and thorough review of the Tennessee High Performance Building Requirements Manual and Checklist, and in accordance with the Tennessee Code Annotated (TCA), The Owner has determined that there are 0 (zero) credits applicable to the scope of the examined project.
Commit to Statement A or B: (Indicate which option is applicable)
Owner's Signature: (Required for A and B) |  |  | Date:
Designer's Signature: (Required for A only) |  |  | Date:
Contractor's Signature: (Required for A only) |  |  | Date:

## MR-Calculator
Materials and Resources Calculator
TN HPBr Appendix B
Instructions
Complete the table below with construction materials items, their associated costs, and percent by weight or volume of recycled content (pre and post-consumer).
Materials Table
Description of Material |  | Total Construction Cost | Labor Cost | Equipment Cost | Material Cost (Less Labor & Equipment) | Resource Reuse (MR3.6) | Recycled Content (MR3.1 & MR3.2) |  |  | Rapidly Renewable Materials (MR3.7) | Regional Materials (MR3.5) |  | Tennessee Produced Materials
[13 empty] | Non-wood Materials (MR3.3) |  |  |  | Wood Materials (MR3.4)
[7 empty] | Post- Consumer | Pre-Consumer | Net Value |  | Regional Materials | Value | Non-wood Materials | Harvested AND Manuf. in TN | Harvested OR Manuf in TN | Value | Harvested AND Manuf. in TN | Harvested OR Manuf in TN | Value
|  | [$] | [$] | [$] | [$] | [$] | [%] by weight | [%] by weight | [$] | [$] | [%] | [$] | [%] | [%] | [%] | [$] | [%] | [%] | [$]
Division
03 | CONCRETE |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
04 | MASONRY |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
05 | METALS |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
06 | WOOD, PLASTICS & COMPOSITES |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
07 | THERMAL / MOISTURE PROTECTION |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
08 | DOORS & WINDOWS (OPENINGS) |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
09 | FINISHES |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
10 | SPECIALTIES |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
| TOTAL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  |  | 0 |  |  | 0
Points
Percentage of Recycled Content (MR3.1 & MR3.2) | [5 empty] | 0% | 0
Percentage of Tennessee Non-wood Materials (MR3.3) | [5 empty] | 0% | 0
Percentage of Tennessee Wood Materials (MR3.4) | [5 empty] | 0% | 0
Percentage of Regional Materials (MR3.5) | [5 empty] | 0% | 0
Resource Reuse Percentage (MR3.6) | [5 empty] | 0% | 0
Rapidly Renewable Materials Percentage (MR3.7) | [5 empty] | 0% | 0

## DL - Instructions
Daylight and Views Calculator
TN HPBr Appendix B
Requirements
Daylight: Achieve a minimum Daylight Factor of 2% (excluding all direct sunlight penetration) in 75% of all space occupied for critical visual tasks, not including copy rooms, storage areas, mechanical, laundry, and other low occupancy support areas. Exceptions include those spaces where tasks would be hindered by the use of daylight or where accomplishing the specific tasks within a space would be enhanced by the direct penetration of sunlight.
Daylit Area: The total floor area that meets the performance requirements for daylighting
Glare Control: Device or control method used to reduce excessively bright sources of light within the visual field that creates discomfort or loss in visibility.
Glazing Area: The entire area taken up by transparent light-transmitting glazing surfaces for the room. The area includes only the rough opening and excludes the frame, sash, and other non-glazed components.
Glazing Factor: The ratio of interior illuminance at a given point on a given plane (usually the work plane) to the exterior illuminance under known overcast sky conditions. LEED uses a simplified approach for its credit compliance calculations. The variables used to determine the daylight factor include the floor area, window area, window geometry, visible transmittance (Tvis) and window height.
Views: Direct line of sight to vision glazing from 90% of all regularly occupied spaces, not including copy rooms, storage areas, mechanical, laundry, and other low occupancy support areas.
Window Geometry: Description of the window types in the room. The ratio is determined by the Window Geometry table.
Instructions
Note: Orange-colored cells are to be completed by Design Team.
1. First, list all regularly-occupied rooms and their associated square footages. Add rows by the Insert/Rows command between the existing rows. For each room, list each window geometry and the associated glazing area, transmittance, and window height factor. Window areas of the same geometry in the same room may be added together. The calculation may require substantial modification to fit a particular project; therefore, refer to the intent of the credit when modifying the spreadsheet. See the High Performance Building Requirements Manual (HPBr) for more information on how to determine access to views. Finally, designate the glare control used for each window geometry using the corresponding letter or letters from the Glare Control Chart. The table automatically calculates the daylight factor for each room.
2. Compare the amount of daylit area to the requirement listed above to determine if the project can qualify for the credit.
3. Using the drawings, highlight those areas in each room from which a direct line of sight through a clear glazed window (mounted on the vertical wall plane) is possible. Consider any obstruction by the wall thickness when figuring views at oblique angles. Window areas below 2’6” and above 7’6” (including daylight glazing, skylights, and roof monitors) do not qualify for the credit. Visually compare the highlighted areas of each room. In rooms that appear close to the required 90%, measure the area highlighted and compare this to the total square footage of that room. For those rooms that reach 90%, insert the TOTAL square footage for the room in Column L. When determining eligible rooms, consider any planned or anticipated tenant improvement permanent walls that will be in place for initial occupancy.
4. Compare the amount of area with sufficient views to the HPB requirement listed above to determine if the project can qualify for the credit.

## DL - Calculator
Daylight and Views Calculator
TN HPBr Appendix B
Glare Control Chart |  |  |  |  | Window Geometry Table
Type | Description |  |  |  | Window Type |  |  | Geometry Factor | Minimum Tvis | Height Factor | Best Practice Glare Control
1 | Fixed exterior shading devices |  |  |  |  | Sidelighting Daylight Glazing |  | 0.1 | 0.7 | 1.4 | Adjustible Blinds Interior light shelves Fixed transluscent exterior shading devices
2 | Light shelf, exterior
3 | Light shelf, interior |  |  |  |  | Sidelighting Vision Glazing |  | 0.1 | 0.4 | 0.8 | Adjustible Blinds Exterior shading devices
4 | Interior blinds
5 | Pull-down shades |  |  |  |  | Toplighting Vertical Monitor |  | 0.2 | 0.4 | 1 | Fixed interior Adjustible exterior blinds
6 | Fritted glazing
7 | Drapes |  |  |  |  | Toplighting Sawtooth Monitor |  | 0.33 | 0.4 | 1 | Fixed interior Exterior louvers
8 | Electronic black-out glazing
[6 empty] | Toplighting Horizontal Skylights |  | 0.5 | 0.4 | 1 | Interior fins Exterior fins Louvers
Daylighting and Views Calculator
Room | Floor Area | Glazing Area | Window Geometry |  | Transmittance (TVIS) |  | Window Height | Daylight Factor |  | Daylit Area | Views | Glare Control
| [SF] | [SF] | Type | Factor | Actual | Min | Factor | Each | Room | [SF] | [SF]
1 |  | 0 | Horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | Horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | Horizontal | 0.5 |  | 0.4 | 1 | 0%
2 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
3 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
4 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
5 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
6 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
7 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
8 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
9 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
10 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
11 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
12 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
13 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
14 |  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0% | 0% | 0
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
|  | 0 | horizontal | 0.5 |  | 0.4 | 1 | 0%
TOTAL | 0 | [8 empty] | 0 | 0
% Occupied Area meeting Daylight Requirements | [9 empty] | 0%
Percentage of Occupied Area with Sufficient Views | [9 empty] | 0%
| Geometry | Min Tvis | Height
Daylight | 0.1 | 0.7 | 1.4
Vision | 0.1 | 0.4 | 0.8
Vertical | 0.2 | 0.4 | 1
Sawtooth | 0.33 | 0.4 | 1
Horizontal | 0.5 | 0.4 | 1

## Sheet1 (hidden)
New Construction
Renovation
Capital Maintenance
New Construction | Renovation | Capital Maintenance
No | Yes | Yes
| No | No