TBR Accessibility 2017 Timeline

| **Project** | **Responsibility** | **Audience** | **Aspirational Deadline** |
| --- | --- | --- | --- |
| System-wide communication on Fall 2016 Course Audits | Dr. Denley | Campus Accessibility Chairs, Chief Academic Officers, Chief Student Affairs Officers, Faculty | January 2017 |
| Syllabi Report to TBR Office of Academic Affairs | Campus Accessibility Chairs | Faculty | March 3, 2017 |
| Conformance Data Entry into TBR AIMT Webpage | Campus Points of Contact for AIMT data | Campus Accessibility Chairs | Ongoing |
| Assess progress of library task force on collaborative model for assessment | Library Task Force | Library Deans/Directors | Spring 2017 meeting |
| Campus Accessibility Chair Meeting | Dr. Denley, Dr. Leming | Campus Accessibility Chairs | May 10, 2017 |
| Universal Design Regional Training Opportunities | TNeCampus, Dr. Leming | Library Deans/Directors, Faculty | Late Spring – Summer 2017 |
| Develop future audit timeline of library resources | Library Task Force | Library Deans/Directors | Summer 2017 |
| Report on all new distributed documents (including syllabi) from Fall 2017 forward are accessible | Campus Accessibility Chairs | Faculty | November 17, 2017 |
| Report on legacy documents and campus plan to progressively remediate | Campus Accessibility Chairs | Faculty | November 17, 2017 |
| Campus Accessibility Self-Audits: Faculty Survey | Chief Academic Officer & Campus Accessibility Teams | Sample of faculty in top 30 courses/Top 5 TCAT programs for survey | November 17, 2017 |
| Campus Accessibility Chair Meeting | Dr. Denley, Dr. Leming | Campus Accessibility Chairs | December 2017 |